## Consolidated Gap Analysis
# | Portal | Page | Component | Type | Frozen Status | MVP Status | Include? | Effort (h) | Priority | Notes
EXECUTIVE
1 | Executive | Dashboard | ExecutiveSummary | Card | Complete | Missing | YES | 8 | P1 | Summary banner with key metrics
2 | Executive | Dashboard | ExecutiveKPI | Widget | Complete | Missing | YES | 12 | P1 | KPI cards with trends
3 | Executive | Dashboard | ExecutiveHealth | Gauge | Complete | Missing | CONDITIONAL | 6 | P2 | Health score visualization
4 | Executive | Dashboard | ExecutiveRisk | Card | Complete | Missing | YES | 8 | P1 | Risk summary card
5 | Executive | Dashboard | ExecutiveInsights | Card | Complete | Missing | NO | 0 | P4 | AI insights - not MVP
6 | Executive | Dashboard | ExecutiveActions | ButtonGroup | Complete | Missing | YES | 4 | P2 | Quick action buttons
7 | Executive | Dashboard | ExecutiveNotifications | List | Complete | Missing | CONDITIONAL | 6 | P3 | Notification feed
GOVERNANCE
8 | Governance | Overview | GovernanceSummary | Card | Complete | Missing | YES | 6 | P1 | Overview metrics card
9 | Governance | Compliance | ComplianceTable | Table | Complete | Missing | YES | 8 | P2 | Compliance status table
10 | Governance | Compliance | ComplianceBadge | Badge | Complete | Missing | YES | 2 | P2 | Status indicator badges
11 | Governance | Policies | PolicyCards | CardGrid | Complete | Missing | YES | 6 | P2 | Policy card grid
12 | Governance | Controls | ControlMatrix | Table | Complete | Missing | YES | 10 | P2 | Control effectiveness matrix
13 | Governance | Exceptions | ExceptionList | Table | Complete | Missing | YES | 6 | P2 | Exception management table
14 | Governance | Risk | RiskMatrix | Chart | Complete | Missing | CONDITIONAL | 12 | P2 | Risk visualization - needs v_batch_risk_index
15 | Governance | Audit | AuditTrail | Table | Complete | Missing | YES | 8 | P2 | Audit log table
16 | Governance | Reports | RegulatoryReports | CardGrid | Complete | Missing | CONDITIONAL | 8 | P3 | Regulatory report cards
MIGRATION
17 | Migration | Overview | MigrationSummary | Card | Complete | Missing | YES | 6 | P1 | Migration metrics card
18 | Migration | Projects | ProjectCards | CardGrid | Complete | Missing | YES | 8 | P1 | Project card grid
19 | Migration | Execution | ExecutionStatus | Table | Complete | Missing | YES | 8 | P1 | Execution tracking table
20 | Migration | Datasets | DatasetTable | Table | Complete | Missing | YES | 6 | P2 | Dataset management table
21 | Migration | Mappings | MappingEditor | Form | Complete | Missing | CONDITIONAL | 16 | P3 | Mapping configuration form
22 | Migration | Schedules | ScheduleList | Table | Complete | Missing | YES | 4 | P2 | Schedule management table
23 | Migration | History | HistoryTable | Table | Complete | Missing | YES | 4 | P2 | Migration history table
24 | Migration | Reports | MigrationReports | CardGrid | Complete | Missing | CONDITIONAL | 6 | P3 | Migration report cards
OPERATIONS
25 | Operations | Dashboard | OpsSummary | Card | Complete | Missing | YES | 6 | P1 | Operations metrics card
26 | Operations | Monitoring | MonitoringCharts | Chart | Complete | Missing | YES | 12 | P2 | Real-time monitoring charts
27 | Operations | Alerts | AlertList | Table | Complete | Missing | YES | 6 | P2 | Alert management table
28 | Operations | Schedules | ScheduleCalendar | Calendar | Complete | Missing | CONDITIONAL | 12 | P3 | Schedule calendar view
29 | Operations | Retry | RetryQueue | Table | Complete | Missing | YES | 4 | P2 | Retry management table
30 | Operations | Health | HealthIndicators | Gauge | Complete | Missing | CONDITIONAL | 8 | P3 | System health indicators
VALIDATION
31 | Validation | Rules | RuleCards | CardGrid | Complete | Missing | YES | 6 | P1 | Rule management cards
32 | Validation | Results | ResultTable | Table | Complete | Missing | YES | 6 | P1 | Validation results table
33 | Validation | Queue | QueueList | Table | Complete | Missing | YES | 4 | P2 | Validation queue table
REPORTS
34 | Reports | Overview | ReportSummary | Card | Complete | Missing | YES | 4 | P2 | Report metrics card
35 | Reports | Executive | ExecutiveReports | CardGrid | Complete | Missing | CONDITIONAL | 8 | P3 | Executive report cards
36 | Reports | Operational | OperationalReports | CardGrid | Complete | Missing | CONDITIONAL | 6 | P3 | Operational report cards
37 | Reports | Migration | MigrationReports | CardGrid | Complete | Missing | CONDITIONAL | 6 | P3 | Migration report cards
38 | Reports | Validation | ValidationReports | CardGrid | Complete | Missing | CONDITIONAL | 4 | P3 | Validation report cards
39 | Reports | Governance | GovernanceReports | CardGrid | Complete | Missing | CONDITIONAL | 4 | P3 | Governance report cards
40 | Reports | Scheduled | ScheduledReports | Table | Complete | Missing | YES | 4 | P2 | Scheduled reports table
41 | Reports | Templates | TemplateCards | CardGrid | Complete | Missing | NO | 0 | P4 | Report templates - not MVP
ADMINISTRATION
42 | Administration | Overview | AdminSummary | Card | Complete | Missing | YES | 4 | P2 | Admin metrics card
43 | Administration | Users | UserTable | Table | Complete | Missing | YES | 6 | P2 | User management table
44 | Administration | Roles | RoleTable | Table | Complete | Missing | YES | 4 | P2 | Role management table
45 | Administration | Tenants | TenantTable | Table | Complete | Missing | CONDITIONAL | 6 | P3 | Tenant management table
46 | Administration | Settings | SettingsForm | Form | Complete | Missing | YES | 8 | P2 | System settings form
47 | Administration | FeatureFlags | FlagList | Table | Complete | Missing | NO | 0 | P4 | Feature flags - not MVP
48 | Administration | Health | HealthDashboard | Chart | Complete | Missing | CONDITIONAL | 8 | P3 | Platform health dashboard
TASK MANAGEMENT
49 | Task Management | Dashboard | TaskSummary | Card | Complete | Missing | YES | 4 | P2 | Task metrics card
50 | Task Management | MyTasks | TaskList | Table | Complete | Missing | YES | 6 | P2 | Personal tasks table
51 | Task Management | Workflows | WorkflowList | Table | Complete | Missing | CONDITIONAL | 8 | P3 | Workflow management table
52 | Task Management | Approvals | ApprovalList | Table | Complete | Missing | CONDITIONAL | 6 | P3 | Approval queue table
53 | Task Management | Calendar | TaskCalendar | Calendar | Complete | Missing | NO | 0 | P4 | Task calendar - not MVP
AUTH
54 | Auth | Login | LoginForm | Form | Complete | Exists | YES | 0 | N/A | Already functional
55 | Auth | Login | PasswordToggle | Button | Complete | Exists | YES | 0 | N/A | Show/hide password toggle
56 | Auth | ForgotPassword | ResetForm | Form | Complete | Missing | CONDITIONAL | 4 | P4 | Needs backend endpoint
57 | Auth | SessionExpired | SessionMessage | Card | Complete | Missing | CONDITIONAL | 4 | P4 | Needs auth interceptor
58 | Auth | AccessDenied | AccessDeniedPage | Card | Complete | Missing | YES | 2 | P1 | Simple static component
59 | Auth | — | AuthInterceptor | Service | Complete | Missing | CONDITIONAL | 16 | P4 | 401 handling service
60 | Auth | — | RBACFilter | Service | Complete | Missing | CONDITIONAL | 16 | P3 | Role-based navigation filtering
THEME
61 | Theme | — | CSSVariables | Config | Complete | Exists | YES | 0 | N/A | 22 color variables - already exists
62 | Theme | — | DarkModeToggle | Toggle | Complete | Exists | YES | 0 | N/A | Moon/Sun toggle - already exists
63 | Theme | — | ThemeApplication | Config | Complete | Exists | YES | 0 | N/A | CSS variable application - already exists
64 | Theme | — | SystemPreference | Service | Complete | Exists | YES | 0 | N/A | prefers-color-scheme detection - already exists
65 | Theme | — | BrandingConfig | Config | Complete | Missing | NO | 0 | P4 | Logo, colors, favicon - not MVP
66 | Theme | — | EnvironmentTheming | Config | Complete | Missing | CONDITIONAL | 8 | P2 | Dev/Testing/Prod color coding
LAYOUT
67 | Layout | — | ApplicationShell | Shell | Complete | Exists | YES | 0 | N/A | App wrapper - already exists
68 | Layout | — | Header | Header | Complete | Exists | YES | 0 | N/A | Top bar - already exists
69 | Layout | — | Sidebar | Navigation | Complete | Exists | YES | 0 | N/A | Collapsible sidebar - already exists
70 | Layout | — | Footer | Footer | Complete | Missing | NO | 0 | P4 | Version, copyright - not MVP
71 | Layout | — | Breadcrumb | Navigation | Complete | Missing | CONDITIONAL | 4 | P2 | Path-based navigation
72 | Layout | — | StatusBar | Bar | Complete | Missing | NO | 0 | N/A | System metrics bar - covered by OperationsPage
73 | Layout | — | EnvironmentBanner | Banner | Complete | Missing | CONDITIONAL | 8 | P2 | Dev/Testing/UAT/Prod indicator
74 | Layout | — | GlobalSearch | Search | Complete | Missing | NO | 0 | P4 | Search overlay - not MVP
75 | Layout | — | NotificationPanel | Panel | Complete | Missing | CONDITIONAL | 12 | P3 | Live notification panel
76 | Layout | — | UserProfileMenu | Menu | Complete | Missing | NO | 0 | N/A | Profile dropdown - covered by RoleSwitcher
77 | Layout | — | LoadingOverlay | Overlay | Complete | Missing | NO | 0 | N/A | Global spinner - per-page loading acceptable
78 | Layout | — | QuickActions | Button | Complete | Missing | NO | 0 | P4 | Floating action button - not MVP
79 | Layout | — | PageHeader | Header | Complete | Missing | NO | 0 | N/A | Per-page header - pages define their own
80 | Layout | — | PageContainer | Container | Complete | Exists | YES | 0 | N/A | Page wrapper - already exists
NAVIGATION
81 | Navigation | — | NavigationConfig | Config | Complete | Exists | YES | 0 | N/A | 8 items - already exists
82 | Navigation | — | MobileNavigation | Drawer | Complete | Exists | YES | 0 | N/A | Responsive drawer - already exists
83 | Navigation | — | NestedChildren | Config | Complete | Missing | NO | 0 | P4 | 100+ sub-items - flat nav preferred for MVP
84 | Navigation | — | SectionGroups | Config | Complete | Missing | NO | 0 | P4 | 4 sections - flat nav preferred for MVP
85 | Navigation | — | RoleBasedFilter | Service | Complete | Missing | CONDITIONAL | 16 | P3 | RBAC filtering for navigation
86 | Navigation | — | SearchIntegration | Service | Complete | Missing | NO | 0 | P4 | GlobalSearch link - not MVP
SUMMARY BY PORTAL
Portal | Total | YES | CONDITIONAL | NO | Exists | Effort (h)
Executive | 7 | 4 | 2 | 1 | 0 | 38
Governance | 9 | 5 | 3 | 1 | 0 | 54
Migration | 8 | 5 | 2 | 1 | 0 | 58
Operations | 6 | 3 | 3 | 0 | 0 | 38
Validation | 3 | 3 | 0 | 0 | 0 | 16
Reports | 8 | 2 | 5 | 1 | 0 | 40
Administration | 7 | 3 | 3 | 1 | 0 | 36
Task Management | 5 | 2 | 2 | 1 | 0 | 24
Auth | 7 | 1 | 4 | 0 | 2 | 42
Theme | 6 | 3 | 1 | 1 | 2 | 8
Layout | 14 | 3 | 4 | 7 | 3 | 24
Navigation | 6 | 2 | 1 | 3 | 2 | 16
TOTAL | 86 | 36 | 30 | 17 | 9 | 394

## Master Gap Analysis
Portal | Component | Frozen Exists | MVP Exists | MVP Status | Frozen Data | MVP Data Relevance % | Existing View/Table | View Relevance % | Better Alternative | New SQL Needed | SQL Statement | Backend Ready | Priority | Include in MVP? | Include Rationale | Effort (h) | MVP File Location | Frozen File Location
Executive Dashboard | ExecutiveSummary (gradient banner) | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | Yes | P1 | YES — 95% | Primary visual anchor; high user impact | 2 | routes/DashboardPage.tsx | portal/executive/ExecutiveSummary.tsx
Executive Dashboard | ExecutiveKPI (5 cards with trends) | Yes | Partial | 4 metric cards, no trends | Mock | 95 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P1 | YES — 90% | Core dashboard metric; trends add value | 4 | routes/DashboardPage.tsx | portal/executive/ExecutiveKPI.tsx
Executive Dashboard | ExecutiveHealth (gauge widget) | Yes | No | Missing | Mock | 0 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P1 | YES — 85% | Visual health indicator; unique to frozen | 3 | routes/DashboardPage.tsx | portal/executive/ExecutiveHealth.tsx
Executive Dashboard | ExecutiveRisk (risk overview) | Yes | No | Missing | Mock | 0 | engine.v_migration_stability_score | 40 | v_batch_risk_index | Yes | CREATE VIEW engine.v_batch_risk_index AS SELECT batch_id, SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) AS risk_score FROM engine.migration_control_summary GROUP BY batch_id; | Blocked | P1 | CONDITIONAL — 70% | Only after v_batch_risk_index created | 3 | routes/DashboardPage.tsx | portal/executive/ExecutiveRisk.tsx
Executive Dashboard | ExecutiveInsights (AI summary) | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P1 | NO — 30% | AI not yet integrated; mock data only | 8 | routes/DashboardPage.tsx | portal/executive/ExecutiveInsights.tsx
Executive Dashboard | ExecutiveActions (6 buttons) | Yes | Partial | 3 link buttons | Mock | 95 | N/A | 0 | N/A | No | N/A | Yes | P1 | YES — 80% | Quick navigation; high usability | 1 | routes/DashboardPage.tsx | portal/executive/ExecutiveActions.tsx
Executive Dashboard | ExecutiveNotifications | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | No | P1 | CONDITIONAL — 60% | Only if notification backend expanded | 4 | routes/DashboardPage.tsx | portal/executive/ExecutiveNotifications.tsx
Executive Dashboard | ExecutiveActivity (recent activity) | Yes | Yes | Implemented | Mock | 95 | engine.migration_control_execution | 95 | N/A | No | N/A | Yes | P1 | EXISTS — 100% | Already implemented | 0 | routes/DashboardPage.tsx | portal/executive/ExecutiveHome.tsx
Migration | MigrationOverview (KPI grid) | Yes | Partial | Simpler implementation | Mock | 70 | engine.migration_batch_registry | 95 | N/A | No | N/A | Partial | P1 | YES — 90% | Core migration summary; high value | 3 | routes/MigrationPage.tsx | portal/migration/MigrationOverview.tsx
Migration | MigrationProjects | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P1 | YES — 85% | Essential for project management | 6 | routes/MigrationPage.tsx | portal/migration/MigrationProjects.tsx
Migration | MigrationExecution (live queue) | Yes | Partial | Uses ValidationPage | Mock | 70 | engine.migration_batch_registry | 95 | N/A | No | N/A | Partial | P1 | YES — 95% | Critical for execution monitoring | 4 | routes/MigrationPage.tsx | portal/migration/MigrationExecution.tsx
Migration | MigrationDatasets | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P1 | YES — 80% | Dataset management is core workflow | 6 | routes/MigrationPage.tsx | portal/migration/MigrationDatasets.tsx
Migration | MigrationMappings | Yes | Yes | Implemented | Mock | 70 | engine.migration_validation_batch | 80 | N/A | No | N/A | Yes | P1 | EXISTS — 100% | Already implemented | 0 | routes/MappingPage.tsx | portal/migration/MigrationMappings.tsx
Migration | MigrationSchedules | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P1 | CONDITIONAL — 50% | Only if scheduler backend built | 8 | routes/MigrationPage.tsx | portal/migration/MigrationSchedules.tsx
Migration | MigrationHistory | Yes | Yes | Implemented | Mock | 70 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P1 | EXISTS — 100% | Already implemented | 0 | routes/ExecutionHistoryPage.tsx | portal/migration/MigrationHistory.tsx
Migration | MigrationReports | Yes | Yes | Implemented | Mock | 70 | engine.migration_control_summary | 85 | N/A | No | N/A | Yes | P1 | EXISTS — 100% | Already implemented | 0 | routes/ReportsPage.tsx | portal/migration/MigrationReports.tsx
Migration | MigrationWorkspace | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P1 | NO — 25% | Complex feature; low priority for MVP | 12 | routes/MigrationPage.tsx | portal/migration/MigrationWorkspace.tsx
Governance | GovernanceOverview (compliance metrics) | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_summary | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/GovernancePage.tsx | portal/governance/GovernanceOverview.tsx
Governance | Policies | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | CONDITIONAL — 55% | Only if policy backend built | 8 | routes/GovernancePage.tsx | portal/governance/Policies.tsx
Governance | ComplianceMonitoring | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_summary | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/GovernancePage.tsx | portal/governance/ComplianceMonitoring.tsx
Governance | RiskGovernance | Yes | Partial | Shows 'No risk data' | Mock | 0 | engine.v_migration_stability_score | 40 | v_batch_risk_index | Yes | CREATE VIEW engine.v_batch_risk_index AS SELECT batch_id, SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) AS risk_score FROM engine.migration_control_summary GROUP BY batch_id; | Blocked | P2 | CONDITIONAL — 70% | Only after v_batch_risk_index created | 3 | routes/GovernancePage.tsx | portal/governance/RiskGovernance.tsx
Governance | RegulatoryReporting | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | NO — 35% | Complex; requires regulatory framework | 12 | routes/GovernancePage.tsx | portal/governance/RegulatoryReporting.tsx
Governance | AuditTrail | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_execution | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/GovernancePage.tsx | portal/governance/AuditTrail.tsx
Governance | ExceptionManagement | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_exceptions | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/GovernancePage.tsx | portal/governance/ExceptionManagement.tsx
Governance | ReleaseGates | Yes | Partial | Shows 'No controls configured' | Mock | 0 | engine.migration_release_decision | 80 | N/A | No | N/A | Yes | P2 | CONDITIONAL — 60% | Only if gate logic expanded | 4 | routes/GovernancePage.tsx | portal/governance/ReleaseGates.tsx
Operations | OperationsDashboard | Yes | Yes | Implemented | Mock | 90 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsDashboard.tsx
Operations | OperationsMonitoring | Yes | Yes | Implemented | Mock | 90 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsMonitoring.tsx
Operations | OperationsAlerts | Yes | Yes | Implemented | Mock | 90 | N/A | 0 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsAlerts.tsx
Operations | OperationsSchedules | Yes | Partial | Shows 'No scheduled tasks' | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | CONDITIONAL — 50% | Only if scheduler backend built | 6 | routes/OperationsPage.tsx | portal/operations/OperationsSchedules.tsx
Operations | OperationsRetry | Yes | Partial | Shows 'No items in retry queue' | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | CONDITIONAL — 55% | Only if retry logic expanded | 4 | routes/OperationsPage.tsx | portal/operations/OperationsRetry.tsx
Operations | OperationsHealth | Yes | Yes | Implemented | Mock | 90 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsHealth.tsx
Operations | OperationsExecution | Yes | Yes | Implemented | Mock | 90 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsExecution.tsx
Operations | OperationsFailures | Yes | No | Missing | Mock | 0 | engine.migration_control_execution | 80 | N/A | No | N/A | Yes | P2 | YES — 75% | Failure details valuable for debugging | 3 | routes/OperationsPage.tsx | portal/operations/OperationsFailures.tsx
Operations | OperationsQueues | Yes | Yes | Implemented | Mock | 90 | engine.migration_batch_registry | 95 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/OperationsPage.tsx | portal/operations/OperationsQueues.tsx
Reports | ReportingOverview | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_summary | 85 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/ReportsPage.tsx | portal/reporting/ReportingOverview.tsx
Reports | ValidationReports | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_summary | 85 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/ReportsPage.tsx | portal/reporting/ValidationReports.tsx
Reports | GovernanceReports | Yes | Yes | Implemented | Mock | 85 | engine.migration_governance_status | 85 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/ReportsPage.tsx | portal/reporting/GovernanceReports.tsx
Reports | RiskScoreReport | Yes | Partial | Shows 'No risk score' | Mock | 0 | engine.v_migration_stability_score | 40 | v_batch_risk_index | Yes | CREATE VIEW engine.v_batch_risk_index AS SELECT batch_id, SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) AS risk_score FROM engine.migration_control_summary GROUP BY batch_id; | Blocked | P2 | CONDITIONAL — 70% | Only after v_batch_risk_index created | 3 | routes/ReportsPage.tsx | portal/reporting/RiskScoreReport.tsx
Reports | ComplianceReport | Yes | Yes | Implemented | Mock | 85 | engine.migration_control_exceptions | 85 | N/A | No | N/A | Yes | P2 | EXISTS — 100% | Already implemented | 0 | routes/ReportsPage.tsx | portal/reporting/ComplianceReport.tsx
Reports | ScheduledReports | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | NO — 40% | Requires scheduler backend | 8 | routes/ReportsPage.tsx | portal/reporting/ScheduledReports.tsx
Reports | ReportTemplates | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | NO — 35% | Complex template engine | 12 | routes/ReportsPage.tsx | portal/reporting/ReportTemplates.tsx
Reports | ReportingWorkspace | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P2 | NO — 25% | Low priority for MVP | 10 | routes/ReportsPage.tsx | portal/reporting/ReportingWorkspace.tsx
Administration | AdministrationOverview | Yes | Yes | Implemented | Mock | 80 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/AdministrationPage.tsx | portal/administration/AdministrationOverview.tsx
Administration | UserManagement | Yes | Yes | Implemented | Mock | 80 | platform.users | 80 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/UsersPage.tsx | portal/administration/UserManagement.tsx
Administration | RoleManagement | Yes | Yes | Implemented | Mock | 80 | platform.roles | 80 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/RolesPage.tsx | portal/administration/RoleManagement.tsx
Administration | TenantManagement | Yes | Partial | Route exists | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | CONDITIONAL — 60% | Only if multi-tenant needed | 6 | routes/AdministrationPage.tsx | portal/administration/TenantManagement.tsx
Administration | SystemSettings | Yes | Yes | Implemented | Mock | 80 | platform.settings | 80 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/SettingsPage.tsx | portal/administration/SystemSettings.tsx
Administration | FeatureFlags | Yes | Yes | Implemented | Mock | 80 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/AdministrationPage.tsx | portal/administration/FeatureFlags.tsx
Administration | PermissionManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 40% | Complex; low priority | 8 | routes/AdministrationPage.tsx | portal/administration/PermissionManagement.tsx
Administration | OrganisationManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Not needed for MVP | 10 | routes/AdministrationPage.tsx | portal/administration/OrganisationManagement.tsx
Administration | NotificationManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 35% | Low priority | 6 | routes/AdministrationPage.tsx | portal/administration/NotificationManagement.tsx
Administration | MaintenanceCentre | Yes | Partial | Basic maintenance tab | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | CONDITIONAL — 50% | Basic maintenance only | 4 | routes/AdministrationPage.tsx | portal/administration/MaintenanceCentre.tsx
Administration | Licensing | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/administration/Licensing.tsx
Administration | JobScheduler | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Requires scheduler backend | 10 | routes/AdministrationPage.tsx | portal/administration/JobScheduler.tsx
Administration | HealthMonitoring | Yes | Yes | Implemented | Mock | 80 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/AdministrationPage.tsx | portal/administration/HealthMonitoring.tsx
Administration | EnvironmentManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 25% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/administration/EnvironmentManagement.tsx
Administration | PlatformConfiguration | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/administration/PlatformConfiguration.tsx
Administration | SubscriptionManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 10 | routes/AdministrationPage.tsx | portal/administration/SubscriptionManagement.tsx
Security | SecurityOverview | Yes | Partial | Static policy display | Mock | 30 | N/A | 0 | N/A | No | N/A | No | P3 | CONDITIONAL — 55% | Basic security status only | 3 | routes/AdministrationPage.tsx | portal/security/SecurityOverview.tsx
Security | AuthenticationPolicies | Yes | Partial | Static display | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | CONDITIONAL — 50% | Only if auth config needed | 4 | routes/AdministrationPage.tsx | portal/security/AuthenticationPolicies.tsx
Security | EncryptionManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/security/EncryptionManagement.tsx
Security | KeyManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/security/KeyManagement.tsx
Security | CertificateManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/security/CertificateManagement.tsx
Security | CredentialManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 25% | Not needed for MVP | 6 | routes/AdministrationPage.tsx | portal/security/CredentialManagement.tsx
Security | IdentityProviders | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 25% | Not needed for MVP | 8 | routes/AdministrationPage.tsx | portal/security/IdentityProviders.tsx
Security | MultiFactorAuthentication | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Not needed for MVP | 6 | routes/AdministrationPage.tsx | portal/security/MultiFactorAuthentication.tsx
Security | SessionManagement | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Not needed for MVP | 4 | routes/AdministrationPage.tsx | portal/security/SessionManagement.tsx
Security | ThreatMonitoring | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 20% | Not needed for MVP | 10 | routes/AdministrationPage.tsx | portal/security/ThreatMonitoring.tsx
Security | AuditLogs | Yes | Yes | In governance audit tab | Mock | 85 | engine.migration_control_execution | 95 | N/A | No | N/A | Yes | P3 | EXISTS — 80% | Already in governance | 0 | routes/GovernancePage.tsx | portal/security/AuditLogs.tsx
Security | ApiSecurity | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 25% | Not needed for MVP | 6 | routes/AdministrationPage.tsx | portal/security/ApiSecurity.tsx
Security | ComplianceStatus | Yes | Yes | In governance compliance tab | Mock | 85 | engine.migration_control_summary | 95 | N/A | No | N/A | Yes | P3 | EXISTS — 80% | Already in governance | 0 | routes/GovernancePage.tsx | portal/security/ComplianceStatus.tsx
Task Management | TaskDashboard | Yes | Yes | Implemented | Mock | 75 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/TaskManagementPage.tsx | portal/task-management/TaskDashboard.tsx
Task Management | AllTasks | Yes | Yes | Implemented | Mock | 75 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/TaskManagementPage.tsx | portal/task-management/AllTasks.tsx
Task Management | MyTasks | Yes | No | Missing | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | CONDITIONAL — 55% | Only if user-specific tasks needed | 4 | routes/TaskManagementPage.tsx | portal/task-management/MyTasks.tsx
Task Management | TaskWorkflows | Yes | Yes | Implemented | Mock | 75 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/WorkflowsPage.tsx | portal/task-management/TaskWorkflows.tsx
Task Management | TaskCalendar | Yes | No | Removed Phase 08C | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Removed as dead feature | 0 | N/A | portal/task-management/TaskCalendar.tsx
Task Management | TaskApprovals | Yes | No | Removed Phase 08C | Mock | 0 | N/A | 0 | N/A | No | N/A | No | P3 | NO — 30% | Removed as dead feature | 0 | N/A | portal/task-management/TaskApprovals.tsx
Task Management | TaskNotifications | Yes | Yes | Implemented | Mock | 75 | N/A | 0 | N/A | No | N/A | Yes | P3 | EXISTS — 100% | Already implemented | 0 | routes/NotificationsPage.tsx | portal/task-management/TaskNotifications.tsx

## SQL Views & Relevance
View Name | Current Use | Relevance % | Assessment | Better Alternative | Proposed SQL | Status
engine.v_migration_stability_score | Risk score in reports | 40 | Pass-rate stability, NOT risk score. Shows % of controls passing, not risk. | v_batch_risk_index | N/A (existing view) | BLOCKED — relevance too low for risk
engine.v_dataset_risk_index | Not used by MVP | 80 | Per-entity risk scoring using FAIL=1, ERROR=2 methodology. Good data but per-entity not per-batch. | Use for entity-level risk detail | N/A (existing view) | AVAILABLE — not yet integrated
engine.v_migration_score_trend | Not used by MVP | 60 | Score trends over time. Could enhance dashboard trend charts. | Use for trend visualization | N/A (existing view) | AVAILABLE — not yet integrated
engine.v_migration_health_dashboard | Not used by MVP | 70 | Health metrics summary. Could enhance dashboard health widget. | Use for health gauge | N/A (existing view) | AVAILABLE — not yet integrated
engine.v_batch_governance_summary | Not used by MVP | 75 | Governance summary per batch. Could enhance governance overview. | Use for governance dashboard | N/A (existing view) | AVAILABLE — not yet integrated
engine.v_rule_failure_analysis | Not used by MVP | 85 | Rule failure analysis. Could enhance validation reports. | Use for failure drill-down | N/A (existing view) | AVAILABLE — not yet integrated
v_batch_risk_index (PROPOSED) | Not yet created | 100 | Per-batch risk scoring using FAIL=1, ERROR=2 methodology from v_dataset_risk_index, aggregated to batch level. | N/A — this IS the replacement | CREATE VIEW engine.v_batch_risk_index AS SELECT batch_id, SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) AS risk_score, CASE WHEN SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) >= 10 THEN 'CRITICAL' WHEN SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) >= 5 THEN 'HIGH' WHEN SUM(CASE WHEN overall_status='FAIL' THEN 1 WHEN overall_status='ERROR' THEN 2 ELSE 0 END) >= 1 THEN 'MEDIUM' ELSE 'LOW' END AS risk_level FROM engine.migration_control_summary GROUP BY batch_id; | PROPOSED — BLOCKED
v_migration_score_summary (PROPOSED) | Not yet created | 95 | Migration score summary per batch with pass rates and control counts. | N/A — this IS the replacement | CREATE VIEW engine.v_migration_score_summary AS SELECT batch_id, COUNT(*) AS total_controls, SUM(CASE WHEN overall_status='PASS' THEN 1 ELSE 0 END) AS passed_controls, ROUND(SUM(CASE WHEN overall_status='PASS' THEN 1 ELSE 0 END) * 100.0 / NULLIF(COUNT(*), 0), 1) AS pass_rate FROM engine.migration_control_summary GROUP BY batch_id; | PROPOSED — BLOCKED

## Portal Summary
Portal | Frozen Files | MVP Files | MVP Completion % | Data Relevance % | Backend Ready | Priority | Total Components | Include YES | Include CONDITIONAL | Include NO | Include EXISTS | Total Effort (h)
Executive Dashboard | 12 | 1 | 60 | 95 | Yes | P1 | 8 | 3 | 2 | 1 | 2 | 25
Migration | 10 | 3 | 45 | 70 | Partial | P1 | 9 | 3 | 1 | 1 | 4 | 30
Governance | 11 | 1 | 70 | 85 | Yes | P2 | 8 | 0 | 3 | 1 | 4 | 15
Operations | 14 | 1 | 75 | 90 | Yes | P2 | 9 | 1 | 2 | 0 | 6 | 13
Reports | 14 | 1 | 65 | 85 | Yes | P2 | 8 | 0 | 1 | 3 | 4 | 33
Administration | 19 | 4 | 50 | 80 | Yes | P3 | 16 | 0 | 3 | 7 | 6 | 76
Security | 17 | 1 | 15 | 30 | No | P3 | 13 | 0 | 2 | 10 | 1 | 73
Task Management | 8 | 3 | 55 | 75 | Yes | P3 | 7 | 0 | 1 | 2 | 4 | 4

## Backend Readiness
Repository | Table/View | Query Type | Data Exists | Used By Frontend | API Endpoint | Endpoint Functional
dashboard_repository | engine.migration_batch_registry | SELECT COUNT, status | Yes | DashboardPage | /api/v1/dashboard/portfolio | Yes
dashboard_repository | engine.control_registry | SELECT COUNT | Yes | DashboardPage | /api/v1/dashboard/portfolio | Yes
dashboard_repository | engine.migration_control_execution | SELECT recent activity | Yes | DashboardPage | /api/v1/dashboard/activity | Yes
execution_history_repository | engine.migration_batch_registry | SELECT paginated list | Yes | ExecutionHistoryPage | /api/v1/execution/history | Yes
execution_history_repository | engine.migration_control_summary | SELECT report data | Yes | ReportsPage | /api/v1/execution/{batch}/report | Yes
execution_history_repository | engine.migration_governance_status | SELECT governance | Yes | ReportsPage | /api/v1/execution/{batch}/governance | Yes
execution_history_repository | engine.migration_control_exceptions | SELECT exceptions | Yes | ReportsPage | /api/v1/execution/{batch}/compliance | Yes
execution_control_repository | engine.migration_batch_registry | SELECT status | Yes | ValidationPage | /api/v1/execution/status/{batch} | Yes
execution_control_repository | engine.batch_execution_checkpoint | SELECT checkpoint | Yes | ExecutionControl | /api/v1/execution-control/lifecycle | Yes
governance_repository | engine.migration_control_execution | SELECT audit entries | Yes | GovernancePage | /api/v1/governance/audit | Yes
governance_repository | engine.migration_release_decision | SELECT approvals | Yes | GovernancePage | /api/v1/governance/approvals | Yes
governance_repository | engine.migration_control_exceptions | SELECT exceptions | Yes | GovernancePage | /api/v1/governance/exceptions | Yes
monitoring_repository | engine.migration_batch_registry | SELECT queue, alerts | Yes | OperationsPage | /api/v1/monitoring/queue | Yes
rule_execution_repository | engine.migration_control_execution | SELECT rule results | Yes | RuleExecution | /api/v1/rule-execution/results | Yes
validation_report_repository | engine.v_migration_stability_score | SELECT risk score | Yes | ReportsPage | /api/v1/execution/{batch}/risk-score | Yes (low relevance)
validation_report_repository | engine.migration_control_exceptions | SELECT compliance | Yes | ReportsPage | /api/v1/execution/{batch}/compliance | Yes

## Effort Estimates
Component | Portal | Include? | Frontend (h) | Backend (h) | Total (h) | Rationale
ExecutiveSummary banner | Executive | YES | 2 | 0 | 2 | Gradient banner; purely visual
ExecutiveKPI with trends | Executive | YES | 4 | 1 | 5 | KPI cards with trend sparklines; need trend data endpoint
ExecutiveHealth gauge | Executive | YES | 3 | 0 | 3 | SVG gauge widget; purely visual
ExecutiveRisk card | Executive | CONDITIONAL | 3 | 4 | 7 | Need v_batch_risk_index view first
ExecutiveInsights AI | Executive | NO | 8 | 8 | 16 | AI not yet integrated
ExecutiveActions buttons | Executive | YES | 1 | 0 | 1 | Quick action buttons; navigation only
ExecutiveNotifications | Executive | CONDITIONAL | 4 | 4 | 8 | Need notification expansion
MigrationProjects | Migration | YES | 6 | 6 | 12 | Project CRUD; need new backend routes
MigrationExecution live | Migration | YES | 4 | 2 | 6 | Live execution queue; enhance existing
MigrationDatasets | Migration | YES | 6 | 6 | 12 | Dataset management; need new backend routes
MigrationSchedules | Migration | CONDITIONAL | 8 | 8 | 16 | Need scheduler backend
MigrationWorkspace | Migration | NO | 12 | 12 | 24 | Complex workspace; low priority
Policies | Governance | CONDITIONAL | 8 | 8 | 16 | Need policy backend
RiskGovernance | Governance | CONDITIONAL | 3 | 4 | 7 | Need v_batch_risk_index view
RegulatoryReporting | Governance | NO | 12 | 12 | 24 | Complex regulatory framework
ReleaseGates | Governance | CONDITIONAL | 4 | 4 | 8 | Need gate logic expansion
OperationsFailures | Operations | YES | 3 | 2 | 5 | Failure detail view; enhance existing
OperationsSchedules | Operations | CONDITIONAL | 6 | 8 | 14 | Need scheduler backend
OperationsRetry | Operations | CONDITIONAL | 4 | 4 | 8 | Need retry logic expansion
RiskScoreReport | Reports | CONDITIONAL | 3 | 4 | 7 | Need v_batch_risk_index view
ScheduledReports | Reports | NO | 8 | 8 | 16 | Need scheduler backend
ReportTemplates | Reports | NO | 12 | 12 | 24 | Complex template engine
ReportingWorkspace | Reports | NO | 10 | 10 | 20 | Low priority
TenantManagement | Admin | CONDITIONAL | 6 | 6 | 12 | Only if multi-tenant needed
PermissionManagement | Admin | NO | 8 | 8 | 16 | Complex permission system
OrganisationManagement | Admin | NO | 10 | 10 | 20 | Not needed for MVP
NotificationManagement | Admin | NO | 6 | 6 | 12 | Low priority
MaintenanceCentre | Admin | CONDITIONAL | 4 | 4 | 8 | Basic maintenance only
Licensing | Admin | NO | 8 | 8 | 16 | Not needed for MVP
JobScheduler | Admin | NO | 10 | 10 | 20 | Need scheduler backend
EnvironmentManagement | Admin | NO | 8 | 8 | 16 | Not needed for MVP
PlatformConfiguration | Admin | NO | 8 | 8 | 16 | Not needed for MVP
SubscriptionManagement | Admin | NO | 10 | 10 | 20 | Not needed for MVP
SecurityOverview | Security | CONDITIONAL | 3 | 2 | 5 | Basic security status
AuthenticationPolicies | Security | CONDITIONAL | 4 | 4 | 8 | Only if auth config needed
EncryptionManagement | Security | NO | 8 | 8 | 16 | Not needed for MVP
KeyManagement | Security | NO | 8 | 8 | 16 | Not needed for MVP
CertificateManagement | Security | NO | 8 | 8 | 16 | Not needed for MVP
CredentialManagement | Security | NO | 6 | 6 | 12 | Not needed for MVP
IdentityProviders | Security | NO | 8 | 8 | 16 | Not needed for MVP
MultiFactorAuthentication | Security | NO | 6 | 6 | 12 | Not needed for MVP
SessionManagement | Security | NO | 4 | 4 | 8 | Not needed for MVP
ThreatMonitoring | Security | NO | 10 | 10 | 20 | Not needed for MVP
ApiSecurity | Security | NO | 6 | 6 | 12 | Not needed for MVP
MyTasks | Task Mgmt | CONDITIONAL | 4 | 2 | 6 | Only if user-specific tasks needed

## Login & Authentication
Item | Frozen Frontend | MVP Frontend | Include in New MVP? | Effort (h) | Priority | Notes
LoginPage | Rich UI: email+password, show/hide toggle, lucide icons, loading state | Functional: email+password, useAuth hook, real API, navigate('/dashboard') | YES — already exists | 0 | N/A | Already functional in MVP
ForgotPasswordPage | Mock form: email input, submit → 'reset email sent' toast, no backend | MISSING | CONDITIONAL — needs backend endpoint | 4 | P4 | Requires /auth/forgot-password backend endpoint
SessionExpiredPage | Clears localStorage → redirect /login with 'Session expired' message | MISSING | CONDITIONAL — needs auth interceptor | 4 | P4 | MVP already handles logout via RoleSwitcher
AccessDeniedPage | 'Access Denied' wrapper (404-style page with icon + 'Go Back' button) | MISSING | YES — simple static component | 2 | P1 | Simple static component, no backend dependency
Auth Interceptor | Session management, token refresh, 401 handling | MISSING | CONDITIONAL — enterprise feature | 16 | P4 | Requires backend auth infrastructure
RBAC Navigation | Navigation filtered by user roles via NavigationContext | All nav visible to authenticated users | CONDITIONAL — enterprise feature | 16 | P3 | Useful for multi-role deployments

## Themes
Item | Frozen Frontend | MVP Frontend | Include in New MVP? | Effort (h) | Priority | Notes
CSS Variables | Comprehensive: 22+ color vars, layout vars, typography, spacing, shadows, transitions | Has variables.css with 22 color vars (same schema: --color-primary-* through --color-*), spacing, typography | YES — already exists | 0 | N/A | Functionally equivalent
Dark Mode Toggle | Header has Moon/Sun toggle → calls setTheme() + localStorage | ThemeToggle.tsx — Moon/Sun toggle, persists to localStorage, respects system preference | YES — already exists | 0 | N/A | Functionally equivalent
Theme Application | theme/light.ts + theme/dark.ts — full theme objects | CSS variables applied via :root/.dark class on <html> | YES — already exists | 0 | N/A | Different approach, same outcome
System Preference Detection | prefers-color-scheme media query | Same — window.matchMedia('(prefers-color-scheme: dark)') | YES — already exists | 0 | N/A | Functionally equivalent
Branding/Customization | Logo, brand colors, custom favicon support | Hardcoded logo, no branding config | NO — not MVP scope | 0 | P4 | Future enhancement
Environment-aware Theming | EnvironmentBanner uses theme-aware colors (dev=blue, testing=yellow, prod=red) | No environment banner | CONDITIONAL — useful for multi-env | 8 | P2 | Requires EnvironmentBanner component
High Contrast Mode | WCAG high contrast support | MISSING | NO — not MVP scope | 0 | P4 | Accessibility enhancement
Custom Theme Upload | Admin can upload custom themes | MISSING | NO — not MVP scope | 0 | P4 | Enterprise feature

## Layout Components
Component | Frozen Frontend | MVP Frontend | Include in New MVP? | Effort (h) | Priority | Notes
ApplicationShell | Wraps all portals: EnvironmentBanner + Header + Sidebar + Breadcrumb + Footer + StatusBar + LoadingOverlay | MISSING (MVP uses Layout.tsx as shell) | NO — MVP has simpler Layout | 0 | N/A | MVP has equivalent in Layout.tsx
Header | Sticky top: GlobalSearch, EnvironmentIndicator, ThemeToggle, RoleSwitcher, NotificationsDropdown, ProfileMenu, LogoutConfirm | MISSING (MVP header is inline in Layout.tsx) | NO — MVP has simpler header | 0 | N/A | MVP has equivalent in Layout.tsx
Sidebar | Collapsible: navigation config, mobile responsive, icons+labels, active state highlighting | DynamicNavigation.tsx — similar collapsible sidebar with icons+labels | YES — already exists | 0 | N/A | Functionally equivalent
Footer | ApplicationFooter: version, copyright, links, API status | MISSING | NO — not critical for MVP | 0 | N/A | Not essential for MVP
Breadcrumb | Auto-generated from current path, click-to-navigate | MISSING | CONDITIONAL — nice-to-have | 4 | P2 | Improves navigation UX
StatusBar | Live system metrics (CPU, memory, response time) — always visible at bottom | MISSING | NO — operational dashboard has this | 0 | N/A | OperationsPage covers this
EnvironmentBanner | Dev/Testing/UAT/Prod banner at top — always visible | MISSING | CONDITIONAL — useful for multi-env | 8 | P2 | Requires environment config API
GlobalSearch | Search portal names, categories, recent searches | MISSING | NO — not critical for MVP | 0 | N/A | Not essential for MVP
NotificationPanel | Live notification list with mark-read, filter by type | NotificationsPage.tsx — full page, not a panel | CONDITIONAL — panel vs page | 12 | P3 | Panel is better UX than page
UserProfileMenu | Profile, preferences, logout, role info | MISSING — RoleSwitcher has logout | NO — MVP has RoleSwitcher | 0 | N/A | RoleSwitcher covers logout
LoadingOverlay | Global loading spinner for transitions | MISSING | NO — individual pages handle loading | 0 | N/A | Per-page loading is acceptable
QuickActions | Floating action button: common tasks | MISSING | NO — not critical for MVP | 0 | N/A | Not essential for MVP
PageHeader | Page title, description, breadcrumb, action buttons | MISSING — pages define their own headers | NO — MVP has simpler approach | 0 | N/A | Per-page headers are acceptable
PageContainer | Consistent page padding, max-width, responsive | PageContainer.tsx — padding, max-width, responsive | YES — already exists | 0 | N/A | Functionally equivalent

## Navigation
Item | Frozen Frontend | MVP Frontend | Include in New MVP? | Effort (h) | Priority | Notes
Navigation Sections | 4 sections: Main, Portals, Operations, System | 1 section: DEFAULT_NAV array (8 items) | YES — MVP has simpler structure | 0 | N/A | MVP covers essentials
Top-level Items | 17 items (Home, Dashboard, Operations, Migration, Validation, Governance, Risk, Reports, Report Centre, Scheduler, Distribution, Task Management, AI Platform, Administration, Security, Settings, Help) | 8 items (Home, Migration, Validation, Governance, Reports, Operations, Tasks, Administration) | PARTIAL — 8 items cover core MVP | 0 | N/A | Additional items added in Phase 08B/08C
Sub-items | 100+ nested children across all portals | DynamicNavigation renders from DEFAULT_NAV (no nested children) | NO — MVP uses flat nav | 0 | N/A | Flat nav is simpler for MVP
Mobile Responsive | Dedicated MobileNavigation component | DynamicNavigation has responsive drawer | YES — already exists | 0 | N/A | Functionally equivalent
Role-based Filtering | Navigation filtered by user roles via NavigationContext | Navigation visible to all authenticated users | CONDITIONAL — enterprise feature | 16 | P3 | Useful for multi-role deployments
Operations Portal | 7 sub-items: Dashboard, Executions, Queues, Schedules, Monitoring, Alerts, Retry Centre | 5 tabs: monitoring, alerts, schedules, retry, health | YES — already exists | 0 | N/A | MVP has equivalent tabs
Migration Portal | 9 sub-items: Overview, Projects, Execution, Datasets, Mappings, Schedules, History, Reports, Workspace | MigrationPage with trigger + status | CONDITIONAL — needs sub-pages | 24 | P1 | Phase 08B recommends adding sub-pages
Validation Portal | 3 sub-items: Rules, Results, Queue | ValidationPage + ValidationResultsPage | YES — already exists | 0 | N/A | Functionally equivalent
Governance Portal | 9 sub-items: Overview, Compliance, Policies, Controls, Exceptions, Risk, Audit, Reports, Workspace | GovernancePage with 6 tabs (overview, compliance, controls, exceptions, risk, audit) | YES — already exists | 0 | N/A | MVP covers 6 of 9 sub-items
Risk Portal | 3 sub-items: Assessment, Register, Matrix | MISSING | CONDITIONAL — needs v_batch_risk_index | 16 | P2 | Blocked by SQL view creation
Reports Portal | 12 sub-items: Overview, Executive, Operational, Migration, Validation, Governance, Audit, Regulatory, Scheduled, Templates, Distribution, Workspace | ReportsPage with 4 tabs (validation, governance, risk, compliance) | CONDITIONAL — needs more tabs | 16 | P2 | Phase 08B recommends adding tabs
Task Management Portal | 7 sub-items: Dashboard, My Tasks, All Tasks, Workflows, Approvals, Calendar, Notifications | TaskManagementPage + TaskDetailPage | CONDITIONAL — needs sub-pages | 12 | P3 | Phase 08B recommends adding sub-pages
AI Platform Portal | 4 sub-items: Assistant, Insights, Recommendations, Report Generator | MISSING | NO — not MVP scope | 0 | P4 | Future enhancement
Security Portal | 15 sub-items: Overview, Credentials, Encryption, Keys, Certificates, Identity Providers, Auth, MFA, Sessions, API Security, Audit Logs, Events, Threats, Compliance, Dashboard | MISSING | NO — not MVP scope | 0 | P4 | Enterprise feature
Administration Portal | 17 sub-items: Overview, Tenants, Organisations, Users, Roles, Permissions, Subscriptions, Licensing, Configuration, Feature Flags, System Settings, Scheduler, Notifications, Environment, Maintenance, Health, Dashboard | AdministrationPage with tabs | YES — already exists | 0 | N/A | MVP covers core admin functions
Settings Portal | 2 sub-items: Profile, Preferences | SettingsPage | YES — already exists | 0 | N/A | Functionally equivalent
Help Portal | 2 sub-items: Documentation, Support | MISSING | NO — not MVP scope | 0 | N/A | Not essential for MVP
Report Centre Portal | 7 sub-items: Home, Explorer, Recent, Favourites, Scheduled, Templates, Workspace | MISSING | NO — not MVP scope | 0 | P4 | Reports portal covers basics
Scheduler Portal | 11 sub-items: Dashboard, Schedules, Calendar, Timeline, Queue, History, Templates, Notifications, Logs, Statistics, Settings | MISSING | NO — not MVP scope | 0 | P4 | OperationsPage covers schedules
Distribution Portal | 13 sub-items: Dashboard, Explorer, Queue, History, Channels, Profiles, Templates, Notifications, Audit, Logs, Statistics, Workspace, Settings | MISSING | NO — not MVP scope | 0 | P4 | Not essential for MVP